## Supplier_Delivery_Log
PO Number | Supplier Code | Supplier Name | Component Code | Component Description | Order Date | Promised Date | Actual Delivery Date | Promised Lead Days | Actual Lead Days | Delivery Status | On Time Flag
PO-9001 | SUP-DE-01 | Krupp Präzision AG | CMP-BRG-88 | Heavy spherical roller bearing 180mm | 2024-01-10 | 2024-02-15 | 2024-02-14 | 36 | 35 | Delivered | TRUE
PO-9002 | SUP-JP-02 | Kyoto Micro-Sensors | CMP-SNS-01 | Piezoelectric vibration transmitter 4-20mA | 2024-01-12 | 2024-02-28 | 2024-03-05 | 47 | 53 | Delivered | FALSE
PO-9003 | SUP-US-03 | Midwest Alloy Forging | CMP-SHF-44 | Precision ground drive shaft 2.5m 4140 steel | 2024-01-18 | 2024-03-15 | 2024-03-12 | 57 | 54 | Delivered | TRUE
PO-9004 | SUP-TW-04 | Hsinchu Silicon Foundry | CMP-DSP-12 | Dual-core industrial DSP microcontroller | 2024-01-20 | 2024-04-10 | 2024-04-18 | 81 | 89 | Delivered | FALSE
PO-9005 | SUP-UK-05 | Vanguard Hydraulics Ltd | CMP-VLV-99 | High-pressure directional proportional valve | 2024-01-25 | 2024-03-01 | 2024-02-28 | 36 | 34 | Delivered | TRUE
PO-9006 | SUP-CH-06 | Alpine Swiss Instruments | CMP-ENC-33 | Optical absolute rotary encoder 24-bit | 2024-02-01 | 2024-03-15 | 2024-03-14 | 43 | 42 | Delivered | TRUE
PO-9007 | SUP-KR-07 | Busan Marine Castings | CMP-IMP-05 | Bronze closed impeller 350mm diameter | 2024-02-05 | 2024-04-05 | 2024-04-12 | 60 | 67 | Delivered | FALSE
PO-9008 | SUP-DE-01 | Krupp Präzision AG | CMP-GRB-14 | Helical bevel gearbox ratio 25:1 | 2024-02-08 | 2024-04-15 | 2024-04-10 | 67 | 62 | Delivered | TRUE
PO-9009 | SUP-SE-08 | Nordic Polymer Seals | CMP-SLS-22 | PTFE spring-energized lip seal pack | 2024-02-12 | 2024-03-05 | 2024-03-04 | 22 | 21 | Delivered | TRUE
PO-9010 | SUP-IT-09 | Modena Precision Gears | CMP-PIN-77 | Carburized spur gear pinion m=6 z=22 | 2024-02-15 | 2024-04-01 | 2024-04-08 | 46 | 53 | Delivered | FALSE
PO-9011 | SUP-US-03 | Midwest Alloy Forging | CMP-FLG-10 | Weld neck ANSI Class 600 flange 8-inch | 2024-02-20 | 2024-03-25 | 2024-03-22 | 34 | 31 | Delivered | TRUE
PO-9012 | SUP-JP-02 | Kyoto Micro-Sensors | CMP-OPT-08 | Infrared optical pyrometer 0-1200C | 2024-02-22 | 2024-04-12 | 2024-04-11 | 50 | 49 | Delivered | TRUE
PO-9013 | SUP-FR-10 | Rhone Carbon Composites | CMP-ROD-55 | Carbon fiber drive linkage rod 1.8m | 2024-02-26 | 2024-04-20 | 2024-04-29 | 54 | 63 | Delivered | FALSE
PO-9014 | SUP-TW-04 | Hsinchu Silicon Foundry | CMP-FPGA-9 | Field programmable gate array 250k LE | 2024-03-01 | 2024-05-15 | 2024-05-14 | 75 | 74 | Delivered | TRUE
PO-9015 | SUP-UK-05 | Vanguard Hydraulics Ltd | CMP-CYL-18 | Double-acting tie rod hydraulic cylinder | 2024-03-05 | 2024-04-15 | 2024-04-12 | 41 | 38 | Delivered | TRUE
PO-9016 | SUP-CH-06 | Alpine Swiss Instruments | CMP-TC-44 | Type K mineral-insulated thermocouple | 2024-03-08 | 2024-04-05 | 2024-04-03 | 28 | 26 | Delivered | TRUE
PO-9017 | SUP-DE-01 | Krupp Präzision AG | CMP-CPL-80 | Flexible disc coupling rated 4500 Nm | 2024-03-10 | 2024-04-25 | 2024-04-23 | 46 | 44 | Delivered | TRUE
PO-9018 | SUP-KR-07 | Busan Marine Castings | CMP-PMP-12 | Submersible slurry pump casing ductile iron | 2024-03-12 | 2024-05-20 | 2024-06-02 | 69 | 82 | Delivered | FALSE
PO-9019 | SUP-SE-08 | Nordic Polymer Seals | CMP-GAS-66 | Spiral wound gasket 316SS with graphite filler | 2024-03-15 | 2024-04-08 | 2024-04-05 | 24 | 21 | Delivered | TRUE
PO-9020 | SUP-IT-09 | Modena Precision Gears | CMP-WRM-03 | Hardened bronze worm drive set ratio 40:1 | 2024-03-18 | 2024-05-02 | 2024-05-09 | 45 | 52 | Delivered | FALSE
PO-9021 | SUP-US-03 | Midwest Alloy Forging | CMP-HUB-29 | Heavy spline hub connector 12-tooth | 2024-03-20 | 2024-05-10 | 2024-05-08 | 51 | 49 | Delivered | TRUE
PO-9022 | SUP-JP-02 | Kyoto Micro-Sensors | CMP-ACC-16 | Triaxial digital accelerometer CANbus | 2024-03-22 | 2024-05-15 | 2024-05-22 | 54 | 61 | Delivered | FALSE
PO-9023 | SUP-FR-10 | Rhone Carbon Composites | CMP-VNE-88 | Composite aerodynamic stator vane set | 2024-03-25 | 2024-05-30 | 2024-05-27 | 66 | 63 | Delivered | TRUE
PO-9024 | SUP-TW-04 | Hsinchu Silicon Foundry | CMP-MCU-04 | Ultra-low-power ARM Cortex-M4 microcontroller | 2024-03-28 | 2024-06-15 | 2024-06-14 | 79 | 78 | Delivered | TRUE
PO-9025 | SUP-UK-05 | Vanguard Hydraulics Ltd | CMP-MNF-11 | Custom machined hydraulic manifold block | 2024-04-01 | 2024-05-20 | 2024-05-17 | 49 | 46 | Delivered | TRUE
PO-9026 | SUP-CH-06 | Alpine Swiss Instruments | CMP-LVDT-02 | Linear displacement sensor stroke 50mm | 2024-04-03 | 2024-05-10 | 2024-05-08 | 37 | 35 | Delivered | TRUE
PO-9027 | SUP-DE-01 | Krupp Präzision AG | CMP-TOR-91 | Dynamic strain gauge torque sensor 10kNm | 2024-04-05 | 2024-06-01 | 2024-05-30 | 57 | 55 | Delivered | TRUE
PO-9028 | SUP-KR-07 | Busan Marine Castings | CMP-NOZ-06 | Hastelloy spray nozzle assembly | 2024-04-08 | 2024-06-15 | 2024-06-25 | 68 | 78 | Delivered | FALSE
PO-9029 | SUP-SE-08 | Nordic Polymer Seals | CMP-RING-44 | Fluoroelastomer O-ring kit high chemical res | 2024-04-10 | 2024-04-30 | 2024-04-28 | 20 | 18 | Delivered | TRUE
PO-9030 | SUP-IT-09 | Modena Precision Gears | CMP-RND-17 | Planetary sun gear precision AGMA 12 | 2024-04-12 | 2024-06-05 | 2024-06-12 | 54 | 61 | Delivered | FALSE
PO-9031 | SUP-US-03 | Midwest Alloy Forging | CMP-ARM-73 | Forged articulated robot pivot arm | 2024-04-15 | 2024-06-20 | 2024-06-17 | 66 | 63 | Delivered | TRUE
PO-9032 | SUP-JP-02 | Kyoto Micro-Sensors | CMP-MAG-09 | Magnetic inductive flow meter sensor tube | 2024-04-18 | 2024-06-25 | 2024-06-24 | 68 | 67 | Delivered | TRUE
PO-9033 | SUP-FR-10 | Rhone Carbon Composites | CMP-BRK-21 | Carbon ceramic high-friction brake disc | 2024-04-20 | 2024-07-01 | 2024-07-09 | 72 | 80 | Delivered | FALSE
PO-9034 | SUP-TW-04 | Hsinchu Silicon Foundry | CMP-PWR-88 | Silicon Carbide (SiC) MOSFET power module | 2024-04-22 | 2024-07-15 | 2024-07-11 | 84 | 80 | Delivered | TRUE
PO-9035 | SUP-UK-05 | Vanguard Hydraulics Ltd | CMP-ACC-50 | Bladder-type nitrogen hydraulic accumulator | 2024-04-25 | 2024-06-15 | 2024-06-12 | 51 | 48 | Delivered | TRUE