## Capital_Projects
Project Code | Project Name | Stage | Strategic Priority | Project Owner | Approved Budget | Committed Cost | Actual Spend | Start Date | Target Completion | Completion Pct | Health Status
PRJ-01 | NextGen Telemetry Grid | Execution | Critical | Marcus Vance | 4500000 | 3800000 | 2900000 | 2023-09-01 | 2024-12-31 | 68% | Green
PRJ-02 | Turbine Insulation Upgrade | Execution | High | Dr. Elena Rostova | 1850000 | 1600000 | 1420000 | 2024-01-15 | 2024-10-31 | 85% | Green
PRJ-03 | Reno Substation Automation | Procurement | High | Tariq Al-Mansoor | 3200000 | 2100000 | 850000 | 2024-03-01 | 2025-06-30 | 30% | Amber
PRJ-04 | Stuttgart Robotics Cell | Testing | Critical | Hans Becker | 5400000 | 5200000 | 4950000 | 2023-06-01 | 2024-08-31 | 92% | Green
PRJ-05 | Tokyo Cleanroom Expansion | Design | Medium | Yuki Tanaka | 2750000 | 450000 | 180000 | 2024-05-15 | 2025-09-30 | 15% | Green
PRJ-06 | Foundry Slag Heat Recovery | Execution | High | Carlos Mendoza | 2100000 | 1950000 | 1800000 | 2023-11-01 | 2024-11-15 | 78% | Amber
PRJ-07 | Hydraulic Press Modernization | Commissioning | Medium | Chloe Dubois | 1450000 | 1420000 | 1390000 | 2023-08-15 | 2024-06-30 | 98% | Green
PRJ-08 | Enterprise SCADA Migration | Execution | Critical | Liam O’Connor | 6800000 | 6100000 | 4800000 | 2023-04-01 | 2025-03-31 | 62% | Red
PRJ-09 | Chilled Water Plant Overhaul | Feasibility | Standard | Sarah Jenkins | 950000 | 80000 | 35000 | 2024-07-01 | 2025-04-30 | 5% | Green
PRJ-10 | Solar Rooftop Microgrid | Execution | Medium | Priya Nair | 3100000 | 2800000 | 2200000 | 2023-10-01 | 2024-12-15 | 72% | Green
PRJ-11 | Autonomous Tugger Fleet | Procurement | High | Kenji Sato | 1650000 | 1100000 | 420000 | 2024-02-01 | 2025-01-31 | 35% | Amber
PRJ-12 | Effluent Treatment Zero Discharge | Design | Critical | Hannah Schmidt | 4200000 | 650000 | 290000 | 2024-04-15 | 2025-11-30 | 18% | Green
PRJ-13 | High-Bay Automated Storage | Execution | High | Zoe Kowalski | 7500000 | 6900000 | 5200000 | 2023-05-01 | 2025-02-28 | 65% | Amber
PRJ-14 | Air Separation Unit Booster | Commissioning | Medium | Amara Okafor | 1900000 | 1880000 | 1850000 | 2023-07-15 | 2024-07-31 | 96% | Green
PRJ-15 | Cryogenic Tank Farm Expansion | Design | Critical | Gabriel Silva | 8200000 | 1200000 | 450000 | 2024-06-01 | 2026-06-30 | 10% | Green
PRJ-16 | Paint Shop VOC Emission Scrubber | Execution | High | David Kim | 2300000 | 2150000 | 1920000 | 2023-12-01 | 2024-10-15 | 82% | Green
PRJ-17 | Vibration Monitoring Retrofit | Testing | Standard | Alice Vance | 780000 | 750000 | 710000 | 2024-01-10 | 2024-08-15 | 88% | Green
PRJ-18 | Emergency Diesel Gen Paralleling | Procurement | High | Marcus Chen | 1350000 | 950000 | 380000 | 2024-03-15 | 2024-12-31 | 40% | Green
PRJ-19 | Laser Cutting Center Cell 4 | Execution | Medium | Dr. Elena Rostova | 2600000 | 2400000 | 1850000 | 2023-10-15 | 2024-11-30 | 74% | Green
PRJ-20 | Raw Material Silo Level Radar | Commissioning | Standard | Tariq Al-Mansoor | 420000 | 415000 | 410000 | 2024-02-01 | 2024-06-30 | 99% | Green
PRJ-21 | Foundry Core Blower Upgrade | Design | High | Hans Becker | 1750000 | 250000 | 95000 | 2024-05-01 | 2025-05-31 | 12% | Amber
PRJ-22 | Distribution Center Conveyor Sorter | Execution | Critical | Yuki Tanaka | 5100000 | 4700000 | 3600000 | 2023-09-15 | 2025-01-15 | 69% | Red
PRJ-23 | Wastewater Reverse Osmosis Skid | Procurement | Medium | Carlos Mendoza | 1250000 | 890000 | 310000 | 2024-04-01 | 2024-12-15 | 32% | Green
PRJ-24 | Plant 3 Compressed Air Loop | Execution | Standard | Chloe Dubois | 890000 | 820000 | 740000 | 2024-01-05 | 2024-09-30 | 86% | Green
PRJ-25 | Digital Twin Predictive Analytics | Testing | High | Marcus Vance | 3400000 | 3250000 | 2980000 | 2023-07-01 | 2024-09-15 | 91% | Green